## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Framework Fanatics | Completed | 34
Project title | Cutting Edge Salon Management & Booking System | In Progress | 1
Stakeholder or organisation | Cuttin Edge Salon | Not Started | 0
Group mentor | Goitsoene Kgwele | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | 2026-08-10 to 2026-08-31 | Overdue | 0
Overall status | Completed
Overall % complete | 95.14% | Contribution Summary | Count
Main achievement | Successfully completed Units 1 and 2 of the project. Developed the complete Initial Software Requirements Specification (SRS) with 19 functional requirements, conducted a comprehensive feasibility study covering all 6 areas (Technical, Operational, Economic, Schedule, Legal, and Ethical), created a project risk register with 10 project-specific risks, and incorporated lecturer-advised enhancements including payment method selection (FR-18) and customer cancellation (FR-08). All group members have practical experience in Flutter, ASP.NET, and Supabase, with 4 members enrolled in the GenAI course for advanced Supabase training. | Contribution entries | 40
Main challenge | Coordinating schedules for the in-person stakeholder interview and translating subjective requirements (e.g., "Luxury" feel) into measurable non-functional requirements. Additionally, incorporating lecturer feedback (payment method and cancellation) required updating the SRS, database schema, and process flows. Managing the scope of 19 functional requirements while ensuring timely completion of all Unit 2 deliverables. One group member not enrolled in the GenAI course, though learnings will be shared across the group. | Verified entries | 40
Next planned activity | Phase 2 | Unverified entries | 0
|  | Stakeholder engagements | 3

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Goitsoene Kgwele | 2026-08-15 | 2026-08-18 | Completed | 100 | Interview notes and photos | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Thabang Zitha | 2026-08-18 | 2026-08-20 | Completed | 100 | SRS -Section 9: Current Process and Diagram | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Thabang Zitha | 2026-08-18 | 2026-08-20 | Completed | 100 |  | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Goitsoene Kgwele , Thabang Zitha | 2026-08-15 | 2026-08-17 | Completed | 100 | SRS Section 4: Purpose, Aim and Objectives, Section 5: Project Scope | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | All members | 2026-08-18 | 2026-08-28 | Completed | 100 | Interview Questions and Responses | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | All members | 2026-08-20 | 2026-08-28 | Completed | 100 | initial SRS document submitted | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Yamkela Mazamane | 2026-08-20 | 2026-08-29 | Completed | 100 | Microsoft Project .mpp file | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Yamkela Mazamane | 2026-08-20 | 2026-08-29 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Nyakallo Pali | 2026-08-20 | 2026-08-29 | Completed | 100 | Supabase Project Setup Screenshot | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Yamkela Mazamane | 2026-08-24 | 2026-08-29 | Completed | 100 | Project progress tracker | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | All members | 2026-08-24 | 2026-08-29 | Completed | 100 | Phase 1 group reflection | Yes |  | Completed
U2-01 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate technical feasibility | Nyakallo Pali | 2026-08-25 | 2026-08-29 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-02 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate operational feasibility | Bennet Linda | 2026-08-25 | 2026-08-30 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-03 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate economic feasibility | All members | 2026-08-25 | 2026-08-30 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-04 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate schedule feasibility | Yamkela Mazamane | 2026-08-25 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-05 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate legal feasibility | Thabang Zitha | 2026-08-25 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-06 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate ethical feasibility | Goitseone kgwele | 2026-08-25 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-07 | Unit 2 / Phase 1 | Activity 2.2 | Complete overall feasibility conclusion | All members | 2026-08-28 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-08 | Unit 2 / Phase 1 | Activity 2.2 | Identify project risks (8-12 risks) | All members | 2026-08-26 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-09 | Unit 2 / Phase 1 | Activity 2.2 | Rate likehood and impact of risks | All members | 2026-08-26 | 2026-08-31 | Completed | 100 | Risk Register with likehood and impact ratings | Yes |  | Completed
U2-10 | Unit 2 / Phase 1 | Activity 2.2 | Identify mitigation and contingency actions | All members | 2026-08-26 | 2026-08-31 | Completed | 100 | Risk Register with mitigation and contigency | Yes |  | Completed
U2-11 | Unit 2 / Phase 1 | Activity 2.2 | Assign risk owners | Goitseoene Kgwele | 2026-08-28 | 2026-08-31 | Completed | 100 | Risk register with owners and status | Yes |  | Completed
U2-12 | Unit 2 / Phase 1 | Activity 2.2 | Identify three highest risks | All members | 2026-08-29 | 2026-08-31 | Completed | 100 | Risk register- Three highest Risk identified | Yes |  | Completed
U2-13 | Unit 2 / Phase 1 | Activity 2.3 | Review feasibility and risk findings | All members | 2026-08-29 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-14 | Unit 2 / Phase 1 | Activity 2.3 | Refine project scope | Thabang Zitha | 2026-08-29 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-15 | Unit 2 / Phase 1 | Activity 2.3 | Update functional requirement | Thabang Zitha | 2026-08-29 | 2026-08-31 | Completed | 100 | Functional Required SRS | Yes |  | Completed
U2-16 | Unit 2 / Phase 1 | Activity 2.3 | Create requirement change log | Thabang Zitha | 2026-08-29 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-17 | Unit 2 / Phase 1 | Activity 2.3 | update database schema | Nyakallo Pali | 2026-08-29 | 2026-08-31 | Completed | 100 | Updated database schema with payment method, cancelled at and cancellation reason | Yes |  | Completed
U2-18 | Unit 2 / Phase 1 | Activity 2.3 | update SRS with Unit 2 work | All members | 2026-08-29 | 2026-08-31 | Completed | 100 | Finalised SRS | Yes |  | Completed
U2-19 | Unit 2 / Phase 1 | Activity 2.3 | Update Microsoft Project schedule | Yamkela Mazamane | 2026-08-29 | 2026-08-31 | Completed | 100 | Microsoft Project .mpp file | Yes |  | Completed
U2-20 | Unit 2 / Phase 1 | Activity 2.3 | Update GitHub repository | Yamkela Mazamane | 2026-08-30 | 2026-09-02 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U2-21 | Unit 2 / Phase 1 | Activity 2.3 | Update Project Progress Tracker | Yamkela Mazamane | 2026-08-31 | 2026-08-31 | Completed | 100 | Project progress tracker | Yes |  | Completed
U2-22 | Unit 2 / Phase 1 | Activity 2.3 | Confirm important changes with stakeholder | Goitsoene Kgwele | 2026-08-28 | 2026-09-02 | In Progress | 25 | Meeting notes to be recorded | Yes |  | On Track
U2-23 | Unit 2 / Phase 1 | Activity 2.3 | Complete Phase 1 group reflection | All members | 2026-08-30 | 2026-08-31 | Completed | 100 | Project progress tracker | Yes |  | Completed
U2-24 | Unit 2 / Phase 1 |  | Powerpoint presentation | All members | 2026-08-30 | 2026-08-31 | Completed | 100 | Phase 1 PowerPoint Presentation | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Goitsoene Kgwele | 221050663 | Unit 1 / Phase 1 | Activity 1.1 | Stakeholder identification and confirmation | Identified and confirmed Cutting Edge Salon as the external stakeholder. Arranged and coordinated the initial stakeholder meeting. | 2026-08-18 | 3 | SRS - Stakeholders and User Groups, Interview photos | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview preparation and conduct | Prepared interview questions. Led the stakeholder interview session. Documented key findings and requirements. | 2026-08-18 | 4 | Interview Questions and Responses, Photos | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | SRS coordination | Coordinated the compilation of the initial SRS document. Ensured all 17 sections were completed. Integrated team contributions. | 2026-08-25 | 6 | Initial SRS Document | Yes | 25/08/2026
|  | Unit 2 / Phase 1 | Activity 2.1 | Ethical feasibility evaluation | Evaluated ethical feasibility. Assessed stakeholder informed consent, data collection necessity, and customer empowerment features. | 2026-08-28 | 2 | Unit 2 documentation | Yes | 29/08/2026
|  | Unit 2 / Phase 1 | Activity 2.2 | Risk register oversight | Oversaw the creation of the risk register. Prepared risk register format. Reviewed all 10 risks for completeness. | 2026-08-29 | 3 | Unit 2 documentation - Risk Registe | Yes | 39/08/2036
|  | Unit 2 / Phase 1 | Activity 2.2 | Phase 1 group reflection coordination | Coordinated and documented the Phase 1 group reflection. Compiled responses from all members. | 2026-08-31 | 2 | Unit 2 documentation - Phase 1 Group Reflection | Yes | 31/08/2036
|  | Unit 2 / Phase 1 | Additional | GenAI course participation | Actively participated in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 31/08/2036 | 4 members enrolled
Thabang Zitha | 223007074 | Unit 1 / Phase 1 | Activity 1.1 | Current process and problem documentation | Documented the current manual process. Created process flow diagram. Wrote the problem statement. | 2026-08-20 | 4 | SRS: Current Process and Diagram | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.1 | Project aim, objectives and scope definition | Defined project aim, 8 objectives, and project scope including deliverables, acceptance criteria, exclusions, constraints, and assumptions. | 2026-08-20 | 3 | SRS - Purpose, Aim and Objectives, Project Scope | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview preparation | Prepared interview questions for stakeholder. Ensured all key areas were covered. | 2026-08-17 | 2 | Interview Questions and Responses | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.3 | Functional requirements documentation | Documented 17 functional requirements. Created requirements prioritisation using MoSCoW method. | 2026-08-24 | 4 | SRS : Functional Requirements, MoSCoW | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.3 | Non-functional requirements documentation | Documented 8 non-functional requirements covering usability, performance, security, availability, and quality. | 2026-08-24 | 2 | SRS: Non-Functional Requirements | Yes | 25/08/2036
|  | Unit 2 / Phase 1 | Activity 2.1 | Legal feasibility evaluation | Evaluated legal feasibility. Assessed data protection, privacy, personal information collection, and GitHub security measures. | 2026-08-28 | 2 | Unit 2 documentation | Yes | 29/08/2036
|  | Unit 2 / Phase 1 | Activity 2.3 | Refine project scope | Refined project scope based on feasibility findings. Documented decisions for each function (Keep, Simplify, Postpone, Remove). | 2026-08-30 | 3 | Unit 2 documentation - Refined Project Scope | Yes | 31/08/2036
|  | Unit 2 / Phase 1 | Activity 2.3 | Update functional requirements (FR-08, FR-18) | Added FR-08 (Customer Cancellation) and FR-18 (Payment Method Selection) as Must Have requirements based on lecturer feedback. Updated MoSCoW prioritisation. | 2026-08-31 | 3 | SRS: Functional Requirements, MoSCoW | Yes | 31/08/2036
|  | Unit 2 / Phase 1 | Activity 2.3 | Create requirements change log | Created comprehensive requirements change log documenting all changes including FR-08 (changed to Must Have), FR-18 (new), FR-09 (simplified), FR-13 (postponed). | 2026-08-31 | 2 | Unit 2 documentation - Requirements Change Lo | Yes | 31/08/2036
|  | Unit 2 / Phase 1 | Additional | GenAI course participation | Actively participated in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 31/08/2036 | 4 members enrolled
Nyakallo Pali | 223060226 | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview participation | Participated in the stakeholder interview. Took notes on technical requirements and backend preferences. | 2026-08-18 | 2 | Interview Questions and Responses | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.3 | Initial SRS - Backend and integration sections | Contributed to SRS sections including System Requirements, Integration Requirements, and Main ASP.NET and Supabase Functions. | 2026-08-25 | 4 | SRS - System Requirements,: Integration Requirements, Main Functions | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.3 | Supabase project setup | Created the initial Supabase project for Cutting Edge SMS. Configured database tables for Users, Bookings, Services, and Stylists. | 2026-08-25 | 3 | Supabase Project Setup Screenshot | Yes | 25/08/2036
|  | Unit 2 / Phase 1 | Activity 2.1 | Technical feasibility evaluation | Led the technical feasibility evaluation. Assessed Flutter, ASP.NET, and Supabase skills. Identified technical strengths and limitations. Determined GenAI course participation benefits. | 2026-08-28 | 4 | Unit 2 documentation - Technical Feasibility | Yes | 29/08/2036
|  | Unit 2 / Phase 1 | Activity 2.2 | Risk identification (R01, R04, R06) | Identified and documented technical risks: R01 (Supabase integration), R04 (integration delays), R06 (email system failure). Provided mitigation and contingency actions. | 2026-08-29 | 3 | Unit 2 documentation - Risk Register | Yes | 29/08/2036
|  | Unit 2 / Phase 1 | Activity 2.3 | Update database schema | Designed and documented database schema updates including payment_method (VARCHAR 10), cancelled_at (TIMESTAMP), and cancellation_reason (VARCHAR 255) fields for the Bookings table. | 2026-08-31 | 3 | Unit 2 documentation - Database Schema Update | Yes | 31/08/2036
|  | Unit 2 / Phase 1 | Activity 2.3 | SRS update - Feasibility section | Integrated the complete feasibility study into the SRS document. Ensured all 6 feasibility areas were properly documented. | 2026-08-31 | 3 | Updated SRS - Feasibility Study | Yes | 31/08/2036
|  | Unit 2 / Phase 1 | Additional | GenAI course participation | Actively participated in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 31/08/2036 | 4 members enrolled
Bennet Linda | 224004294 | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview participation | Participated in the stakeholder interview. Took notes on frontend requirements, UI preferences, and "Luxury" brand expectations. | 2026-08-18 | 2 | Interview Questions and Responses | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.3 | Initial SRS - Frontend and UI sections | Contributed to SRS sections including Product Perspective, Main Flutter Functions, and User Interface requirements. | 2026-08-25 | 4 | SRS - Product Perspective, : Main Functions | Yes | 25/08/2036
|  | Unit 2 / Phase 1 | Activity 2.1 | Operational feasibility evaluation | Led the operational feasibility evaluation. Assessed whether the proposed solution works for the stakeholder and intended users. Evaluated suitability for target users (ages 10-30). | 2026-08-28 | 4 | Unit 2 documentation, Operational Feasibility | Yes | 29/08/2036
|  | Unit 2 / Phase 1 | Activity 2.2 | Risk identification (R04, R07) | Identified and documented technical risks: R04 (integration between Flutter, ASP.NET, and Supabase) and R07 (Google Maps API quota limitations). | 2026-08-29 | 2 | Unit 2 documentation - Risk Register | Yes | 29/08/2036
|  | Unit 2 / Phase 1 | Activity 2.3 | SRS update - Refined project scope | Documented the refined project scope with decisions for each function: Keep (14 requirements), Simplify (FR-09), Postpone (FR-13). | 2026-08-31 | 3 | Unit 2 documentation - Refined Project Scope | Yes | 31/08/2036
Yamkela Mazamani | 224007421 | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview participation | Participated in the stakeholder interview. Documented interview findings and organised stakeholder evidence. | 2026-08-18 | 2 | Interview Questions and Responses, Photos | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.3 | Microsoft Project schedule creation | Created the initial Microsoft Project schedule with tasks, dates, durations, responsibilities, dependencies, and milestones. | 2026-08-25 | 4 | Microsoft Project .mpp file | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.3 | GitHub repository creation | Created and configured the GitHub repository. Set up folder structure. Added README and initial documentation | 2026-08-23 | 3 | https://github.com/Yamkela47/Group-B-.git | Yes | 25/08/2036
|  | Unit 1 / Phase 1 | Activity 1.3 | Progress report and contribution record | Completed the progress report and contribution record for Unit 1. Documented all team contributions. | 2026-08-25 | 2 | Project Progress Tracker - Unit 1 | Yes | 25/08/2036
|  | Unit 2 / Phase 1 | Activity 2.1 | Schedule feasibility evaluation | Evaluated schedule feasibility. Assessed whether all work can be completed within the semester. Identified time constraints and required changes. | 2026-08-28 | 3 | Unit 2 documentation - Schedule Feasibility | Yes | 29/08/2036
|  | Unit 2 / Phase 1 | Activity 2.2 | Risk register formatting | Formatted the risk register. Created the risk register table with all 10 risks, likelihood, impact, scores, mitigation, contingency, owners, and status. | 2026-08-29 | 3 | Unit 2 documentation - Risk Register | Yes | 29/08/2036
|  | Unit 2 / Phase 1 | Activity 2.3 | Microsoft Project schedule update | Updated the Microsoft Project schedule to reflect Unit 2 progress and refined scope. Added new tasks for FR-08 and FR-18 implementation. | 2026-08-31 | 4 | Updated Microsoft Project .mpp file | Yes | 31/08/2036
|  | Unit 2 / Phase 1 | Activity 2.3 | GitHub repository maintenance | Maintained the GitHub repository. Added Unit 2 documentation, feasibility study, risk register, and updated SRS. | 2026-08-31 | 3 | https://github.com/Yamkela47/Group-B-.git | Yes | 31/08/2036
|  | Unit 2 / Phase 1 | Activity 2.3 | Project Progress Tracker update | Updated the Project Progress Tracker for Unit 2. Recorded task progress, individual contributions, challenges, and actions. | 2026-08-31 | 3 | Updated Project Progress Tracker | Yes | 31/08/2036
|  | Unit 2 / Phase 1 | Additional | GenAI course participation | Actively participated in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 31/08/2036 | 4 members enrolled

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-18 | Unit 1 / Phase 1 | Meeting | Conduct initial stakeholder interview to identify the problem, gather requirements, understand current process, and confirm stakeholder needs and expectations. | All members | Cutting Edge Salon Owner / Manager | • Salon Name: Cutting Edge • Established: 11 April 2022 • Main Problem: "To alleviate mismanagement of daily store running" • Main Goals: "To showcase our products and services and to allow for a smooth booking system" • Target Audience: 10-30 years old, everyone (Men, Women, Children) • Core Services: Hair cutting, hair colouring, beard shaving, hot towel treatment • Brand Vibe: "Luxury" • Competitor: Legendary Barber • Desired Pages: Home, About Us, Services, Pricing, Our Team, Gallery, Booking • Operating Hours: Weekdays 9-6, Saturdays 8:30-5, Sundays 08:30-13:00 • Address: 10 Melck Street, Pioneer Building, Welkom Central • Contact: 0787676599 / cutinged@88@gmail.com • Stylists: All offer the same services • WhatsApp for Bookings: NO (confirmed) • Services: Standard haircut = 40 min, Cut & Dye = 1h 15min | Document all findings in SRS. Begin development of Initial Software Requirements Specification (SRS). | Interview Questions and Responses (Full Transcript) Interview Meeting Evidence (Photos) Interview notes, meeting records
2026-08-18 | Unit 1 / Phase 1 | Requirements confirmation | Summarise main findings and confirm that the group's understanding of the stakeholder's needs and requirements is correct. | All members | Cutting Edge Salon Owner / Manager | Confirmed Findings: • The current manual diary system is inefficient and causes mismanagement • The stakeholder wants customers to book online • The stakeholder wants a "Luxury" feel • The stakeholder does NOT want WhatsApp bookings • The stakeholder has stylists who all offer the same services • The stakeholder wants pages: Home, About Us, Services, Pricing, Our Team, Gallery, Booking • Promote "Cut and Dye" as the flagship service | Proceed with SRS development based on confirmed requirements. | Appendix C: Stakeholder Confirmation of Findings Summary notes
31 Aug - 2 Sep 2026 | Unit 2 / Phase 1 | Scope change discussion | Present and discuss lecturer-advised scope changes and new requirements: FR-08 (Customer Cancellation) and FR-18 (Payment Method Selection - Cash/Card). | Goitseone Kgwele, Thabang Zitha | Cutting Edge Salon Owner / Manager | Pending confirmation Proposed Changes to Discuss: • FR-08: Customer cancellation functionality (lecturer-advised) • FR-18: Payment method selection (cash or card) - lecturer-advised • FR-09: Email reminders simplified to manual reminders • FR-13: Gallery display postponed to Phase 2 • Scope refinement based on feasibility study findings Reasons: Lecturer feedback; ensures comprehensive functionality; improves customer experience and staff efficiency | Record stakeholder comments. Confirm acceptance of changes. Update SRS accordingly. Document meeting notes and confirmation. | Meeting notes to be recorded Email confirmation or WhatsApp communication
2026-09-02 | Unit 2 / Phase 1 | Final scope confirmation | Confirm all scope changes and refined project scope with stakeholder. Obtain final approval. | Goitseone Kgwele, Thabang Zitha | Cutting Edge Salon Owner / Manager | Pending confirmation Final Scope to Confirm: • 14 Must Have requirements including FR-08 and FR-18 • 4 Should Have requirements • FR-13 (Gallery) postponed to Phase 2 • FR-09 (Email reminders) simplified to manual reminders • Database schema updates: payment_method, cancelled_at, cancellation_reason • Refined project scope and deliverables | Obtain stakeholder confirmation. Document final decisions. Update SRS with confirmed changes. | Confirmation summary Signed confirmation (if available) Email or WhatsApp communication

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-18 | Unit 1 / Phase 1 | Coordinating schedules for the in-person stakeholder interview due to conflicting availability of all group members and stakeholder. | Delayed the stakeholder interview by 2 days. Affected the start of requirements documentation. | Rescheduled interview to a mutually convenient date. Communicated with stakeholder via multiple channels (call, WhatsApp, email) to confirm availability. Assigned Goitseone as primary contact. | Goitseone Kgwele | 2026-08-18 | Resolved
2026-08-18 | Unit 1 / Phase 1 | Translating subjective stakeholder requirements (e.g., "Luxury" feel) into measurable non-functional requirements. | Potential ambiguity in requirements could lead to misinterpretation during development. | Conducted detailed follow-up questions during interview. Documented specific UI/UX expectations (e.g., elegant colour scheme, premium feel, smooth animations). Referenced brand colours and materials provided by stakeholder. | Thabang Zitha | 2026-08-20 | Resolved
2026-08-25 | Unit 2 / Phase 1 | Supabase integration confidence - the group has practical experience but recognises the need for enhanced skills. | Could delay backend integration and database operations during development phase. | Four members enrolled in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. Shared learning across the entire group. Created plan to test basic integration early. | Nyakallo Pali | Ongoing | Resolved
2026-08-26 | Unit 2 / Phase 1 | Managing the expanded scope of 19 functional requirements (17 original + 2 new additions). | Risk of scope creep; could prevent prototype completion within the semester. | Conducted MoSCoW prioritisation analysis. Identified 14 Must Have requirements (including FR-08 and FR-18) and 4 Should Have requirements. Postponed FR-13 (Gallery) to Phase 2. Simplified FR-09 (Email reminders) to manual reminders. | Thabang Zitha | 2026-08-31 | Resolved
2026-08-27 | Unit 2 / Phase 1 | Incorporating lecturer feedback (FR-08: Customer Cancellation, FR-18: Payment Method Selection) requiring updates to SRS, database schema, and process flows. | Required significant updates to existing documentation. Potential schedule impact. | Added FR-08 and FR-18 as Must Have requirements. Updated SRS Updated database schema with paymentmethod, cancelledat, and cancellation reason fields. Created requirements change log. | Thabang Zitha, Nyakallo Pali | 2026-08-31 | Resolved
2026-08-27 | Unit 2 / Phase 1 | One group member (Yamkela Mazamani) not enrolled in the GenAI course for Supabase enhancement. | Knowledge gap may affect Supabase integration contributions from that member. | Group agreed to share all GenAI learnings with non-enrolled member. Scheduled knowledge transfer sessions during weekly meetings. All group members committed to supporting each other. | All Members | Ongoing | In Progress
2026-08-28 | Unit 2 / Phase 1 | Risk of unequal participation and poor communication affecting project progress and quality. | Could cause delays, incomplete tasks, and reduced quality of deliverables. | Established weekly group progress meetings (every Monday). Record tasks and contributions in Project Progress Tracker. Maintain daily WhatsApp group for communication. Assigned clear tasks with deadlines. Escalation process established if concerns arise. | Goitseone Kgwele | 2026-08-31 | In Progress
2026-08-29 | Unit 2 / Phase 1 | Limited time available for testing and corrections in the development schedule. | Could affect prototype quality and stakeholder acceptance. | Allocated dedicated testing time in Microsoft Project schedule (1.5 weeks). Developed test cases early. Prioritised critical functionality testing. Simplified features where necessary to reduce testing burden. | Yamkela Mazamani | 2026-08-31 | Resolved
2026-08-31 | Unit 2 / Phase 1 | Stakeholder confirmation of scope changes still pending. | Cannot finalise SRS until stakeholder approves new features and scope changes. | Scheduled meeting with stakeholder for 31 Aug - 2 Sep 2026. Prepared presentation of changes and reasons (lecturer feedback, feasibility findings). Will document stakeholder response and update SRS accordingly. | Goitseone Kgwele | 2026-09-02 | In Progress
2026-08-31 | Unit 2 / Phase 1 | Balancing stakeholder expectations with realistic deliverables based on feasibility findings. | Risk of stakeholder dissatisfaction if features are postponed or removed. | Prepared clear rationale for all scope changes based on feasibility study findings. Will present benefits of core functionality first. Emphasised that postponed features (FR-13) can be added later. | Thabang Zitha | 2026-09-02 | In Progress

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 2026-08-10 to 2026-08-31 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Successfully completed Units 1 and 2 of the project. Developed the complete Initial Software Requirements Specification (SRS) with 19 functional requirements (17 original + 2 new). Conducted a comprehensive feasibility study covering all 6 areas (Technical, Operational, Economic, Schedule, Legal, and Ethical). Created a project risk register with 10 project-specific risks with likelihood, impact, mitigation, contingency, owners, and status. Completed a SWOT analysis. Incorporated lecturer-advised enhancements including payment method selection (FR-18) and customer cancellation (FR-08). Updated database schema with payment_method, cancelled_at, and cancellation_reason fields. Created requirements change log and refined project scope. Updated Microsoft Project schedule, GitHub repository, and Project Progress Tracker. Prepared Phase 1 PowerPoint presentation. All group members have practical experience in Flutter, ASP.NET, and Supabase, with 4 members enrolled in the GenAI course for advanced Supabase training. | Stakeholder engagement recorded | Yes
What remains incomplete? | Stakeholder confirmation of scope changes (FR-08: Customer Cancellation, FR-18: Payment Method Selection) is still pending. One group member (Yamkela Mazamani) not enrolled in the GenAI course, though learnings will be shared. Individual confidential peer check not yet completed. | Challenges and actions updated | Yes
Why is it incomplete? | Stakeholder confirmation meeting scheduled for 31 August - 2 September 2026. Yamkela's GenAI course non-enrolment due to personal scheduling reasons; group will share learnings. Individual peer check is a confidential assessment to be completed individually. | Group reflection completed | Yes
Which contributions were particularly important? | Nyakallo Pali (ASP.NET Lead): Technical feasibility evaluation, Supabase setup, database schema update, risk identification (R01, R04, R06). Bennet Linda (Flutter Lead): Operational feasibility evaluation, risk identification (R04, R07), refined project scope. Thabang Zitha (Requirements Analyst): Functional and non-functional requirements, MoSCoW prioritisation, FR-08 and FR-18 implementation, requirements change log, legal feasibility. Goitseone Kgwele (Facilitator): Stakeholder engagement, ethical feasibility, risk register oversight, Phase 1 group reflection coordination. Yamkela Mazamani (Documentation): GitHub repository, Microsoft Project schedule, Project Progress Tracker, schedule feasibility, risk register formatting | Microsoft Project updated | Yes
Were there participation concerns? | No. All group members have participated actively and contributed meaningfully to their assigned responsibilities. The group has worked well together with regular communication through WhatsApp and scheduled meetings. Tasks have been distributed according to individual skills and interests: 3 members strong with coding focus on technical implementation, while 2 members handle documentation and design. | GitHub evidence available | Yes
What will the group improve in the next phase? | 1. Apply learning from the GenAI course for effective Supabase integration 2. Share GenAI learnings with the non-enrolled member 3. Ensure regular progress monitoring through weekly meetings 4. Maintain the risk register and update it as the project progresses 5. Document contributions for assessment evidence 6. Communicate more frequently about technical challenges 7. Implement cancellation logic carefully to ensure availability is restored correctly 8. Design intuitive UI for payment method selection and cancellation 9. Start development early to allow sufficient testing time 10. Conduct more frequent stakeholder check-ins during development | Confidential peer check completed | Yes
Main priority for the next phase | Unit 3: System Architecture and Design - System architecture design, database design, UI/UX design, API design, and integration planning. Additionally, obtain stakeholder confirmation of scope changes and commence development activities.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 2 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Cutting Edge Salon Management & Booking System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The most important learning was understanding the critical importance of early and thorough stakeholder engagement and honest scope assessment. We learned that translating subjective stakeholder requirements (like "luxury" feel) into measurable non-functional requirements requires careful questioning and documentation. Additionally, we discovered that realistic feasibility assessment is essential - we initially wanted to deliver all 17 requirements, but the feasibility study revealed that technical and schedule limitations required us to prioritise and make difficult decisions about what could realistically be delivered within the semester. The lecturer feedback (payment method selection and customer cancellation) taught us to be adaptable and responsive to valuable input. Finally, the GenAI course participation by four members showed us the value of continuous professional development and knowledge sharing. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Stakeholder engagement went exceptionally well. We successfully conducted an in-person interview with the salon owner, confirming all requirements and gathering valuable insights about the problem. Team collaboration was effective, with regular communication through WhatsApp and scheduled meetings. Tasks were distributed according to individual skills: 3 members strong with coding focused on technical implementation, while 2 members handled documentation and design. The feasibility study was comprehensive and honest, evaluating all 6 areas thoroughly. The risk register with 10 project-specific risks was completed successfully with clear mitigation and contingency actions. Incorporating lecturer feedback (FR-08 and FR-18) was handled efficiently. The GenAI course participation by four members demonstrated the group's commitment to professional development. Overall, we completed all Unit 1 and Unit 2 deliverables on schedule. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Scope management was the most difficult aspect. We started with 17 requirements, then added 2 more based on lecturer feedback (FR-08 and FR-18), bringing the total to 19. Deciding which features to postpone (FR-13: Gallery) or simplify (FR-09: Email reminders) was challenging because we wanted to deliver everything but had to be realistic about our capabilities and time constraints. Coordinating schedules for the stakeholder interview was also difficult due to conflicting availability of all group members and the stakeholder. Translating subjective stakeholder requirements (e.g., "Luxury" feel) into measurable non-functional requirements required careful questioning and documentation. Supabase integration is an area where we have practical experience but recognise the need for enhanced skills, which is why four members enrolled in the GenAI course. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided according to individual skills and interests. Goitseone Kgwele led stakeholder engagement, SRS coordination, and risk register oversight. Thabang Zitha focused on requirements analysis, MoSCoW prioritisation, and scope refinement. Nyakallo Pali led technical feasibility, Supabase setup, and database schema updates. Bennet Linda led operational feasibility and frontend planning. Yamkela Mazamani handled documentation, GitHub maintenance, and Microsoft Project updates. This division allowed us to leverage each member's strengths effectively.
Did all members contribute fairly? Explain. | Yes, all members contributed fairly and meaningfully. Each member completed their assigned tasks on time and to a high standard. The 3 members strong with coding (Nyakallo, Bennet, and Goitseone) focused on technical aspects, while the 2 members skilled in documentation (Thabang and Yamkela) ensured high-quality project documentation. Regular check-ins and the Project Progress Tracker helped ensure accountability. All members participated in group meetings and contributed to the feasibility study, risk register, and group reflection. The only minor gap is that one member (Yamkela) is not enrolled in the GenAI course, but the group has committed to sharing all learnings.
How did the group handle disagreements or delays? | Disagreements were handled through open discussion during group meetings. For example, when deciding which features to postpone, we had productive discussions and reached consensus through the MoSCoW prioritisation method. Delays were managed proactively: when the stakeholder interview had to be rescheduled, we communicated with the stakeholder promptly and adjusted our timeline. When lecturer feedback required additional work (FR-08 and FR-18), we absorbed the extra work by reassigning tasks and extending working hours. The group's collaborative approach and commitment to open communication helped resolve all issues constructively.
What did the group learn from the stakeholder? | We learned that Cutting Edge Salon faces significant operational challenges due to its manual booking system. The stakeholder's primary goal is to "alleviate mismanagement of daily store running" and provide a "luxury" customer experience. We learned that the target market (ages 10-30) expects digital convenience and self-service booking capabilities. The stakeholder values the "Cut and Dye" service as the flagship offering and wants to promote it prominently. We also learned that the stakeholder explicitly does not want WhatsApp bookings. Additionally, we learned the importance of understanding the "luxury" brand identity and how to translate it into a digital experience.
Improvement action 1 for the next phase | Apply GenAI learning for effective Supabase integration. Four members have enrolled in the GenAI course conducted by Ms Lonergan. We will actively apply the learning from this course to build confidence and practical skills with Supabase integration. We will share this knowledge with the non-enrolled member through weekly knowledge transfer sessions. This will ensure smooth integration between Flutter, ASP.NET, and Supabase.
Improvement action 2 for the next phase | Increase frequency of progress monitoring and risk register reviews. While we held weekly meetings during Units 1 and 2, we will increase the frequency of progress checks during the development phase. We will review the risk register weekly and update it as the project progresses. We will also ensure that the non-enrolled member is fully upskilled through shared learnings. This will help us identify and address issues early, maintain momentum, and ensure we stay on schedule.
Priority for the next phase | Unit 3: System Architecture and Design. Our priority is to design the system architecture, database design, UI/UX design, API design, and integration planning. We must also obtain stakeholder confirmation of the scope changes (FR-08 and FR-18) and commence development activities. Additionally, we will share all GenAI learnings with the non-enrolled member to ensure the whole group is prepared for development.