## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Framework Fanatics | Completed | 86
Project title | Cutting Edge Salon Management & Booking System | In Progress | 0
Stakeholder or organisation | Cutting Edge Salon | Not Started | 0
Group mentor | Goitsoene Kgwele | Delayed | 0
Reporting phase | Unit 4 / Phase 3 | Blocked | 0
Reporting period | 2026-10-01 to 2026-10-25 | Overdue | 0
Overall status | Completed
Overall % complete | 96.35% | Contribution Summary | Count
Main achievement | Successfully completed the full system architecture and design for the Cutting Edge Salon Management & Booking System. Produced a System Architecture Diagram showing the shared Flutter mobile app (Customer/Stylist roles), ASP.NET Manager Portal, and Supabase backend as one integrated system. Developed Use Case Diagrams for Customer, Stylist and Manager roles with system boundary, associations, <<include>>, <<extend>> and generalization. Created three Sequence Phase 3 focus: complete and verify the integrated Flutter customer/stylist application, ASP.NET manager portal, and shared Supabase backend. Core acceptance priorities are end-to-end booking, double-booking prevention, customer cancellation, cash/card-on-arrival preference, manager booking management, and complete documentation. Progress percentages remain at 0 until the group verifies actual work and records evidence. | Contribution entries | 85
Main challenge | Main delivery risks: integration defects across Flutter, ASP.NET and Supabase; booking conflict/cancellation edge cases; insufficient time for regression testing and documentation before 25 October. Mitigate by prioritising Must Have requirements, testing end-to-end early, assigning owners, and attaching evidence to each completed task. | Verified entries | 85
Next planned activity | Phase 3 focus: complete and verify the integrated Flutter customer/stylist application, ASP.NET | Unverified entries | 0
|  | Stakeholder engagements | 4

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag | Column1
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Goitsoene Kgwele | 2026-08-15 | 2026-08-18 | Completed | 100 | Interview notes and photos | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Thabang Zitha | 2026-08-18 | 2026-08-20 | Completed | 100 | SRS -Section 9: Current Process and Diagram | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Thabang Zitha | 2026-08-18 | 2026-08-20 | Completed | 100 |  | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Goitsoene Kgwele , Thabang Zitha | 2026-08-15 | 2026-08-17 | Completed | 100 | SRS Section 4: Purpose, Aim and Objectives, Section 5: Project Scope | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | All members | 2026-08-18 | 2026-08-28 | Completed | 100 | Interview Questions and Responses | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | All members | 2026-08-20 | 2026-08-28 | Completed | 100 | initial SRS document submitted | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Yamkela Mazamane | 2026-08-20 | 2026-08-29 | Completed | 100 | Microsoft Project .mpp file | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Yamkela Mazamane | 2026-08-20 | 2026-08-29 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Nyakallo Pali | 2026-08-20 | 2026-08-29 | Completed | 100 | Supabase Project Setup Screenshot | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Yamkela Mazamane | 2026-08-24 | 2026-08-29 | Completed | 100 | Project progress tracker | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | All members | 2026-08-24 | 2026-08-29 | Completed | 100 | Phase 1 group reflection | Yes |  | Completed
U2-01 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate technical feasibility | Nyakallo Pali | 2026-08-25 | 2026-08-29 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-02 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate operational feasibility | Bennet Linda | 2026-08-25 | 2026-08-30 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-03 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate economic feasibility | All members | 2026-08-25 | 2026-08-30 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-04 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate schedule feasibility | Yamkela Mazamane | 2026-08-25 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-05 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate legal feasibility | Thabang Zitha | 2026-08-25 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-06 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate ethical feasibility | Goitseone kgwele | 2026-08-25 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-07 | Unit 2 / Phase 1 | Activity 2.2 | Complete overall feasibility conclusion | All members | 2026-08-28 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-08 | Unit 2 / Phase 1 | Activity 2.2 | Identify project risks (8-12 risks) | All members | 2026-08-26 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-09 | Unit 2 / Phase 1 | Activity 2.2 | Rate likehood and impact of risks | All members | 2026-08-26 | 2026-08-31 | Completed | 100 | Risk Register with likehood and impact ratings | Yes |  | Completed
U2-10 | Unit 2 / Phase 1 | Activity 2.2 | Identify mitigation and contingency actions | All members | 2026-08-26 | 2026-08-31 | Completed | 100 | Risk Register with mitigation and contigency | Yes |  | Completed
U2-11 | Unit 2 / Phase 1 | Activity 2.2 | Assign risk owners | Goitseoene Kgwele | 2026-08-28 | 2026-08-31 | Completed | 100 | Risk register with owners and status | Yes |  | Completed
U2-12 | Unit 2 / Phase 1 | Activity 2.2 | Identify three highest risks | All members | 2026-08-29 | 2026-08-31 | Completed | 100 | Risk register- Three highest Risk identified | Yes |  | Completed
U2-13 | Unit 2 / Phase 1 | Activity 2.3 | Review feasibility and risk findings | All members | 2026-08-29 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-14 | Unit 2 / Phase 1 | Activity 2.3 | Refine project scope | Thabang Zitha | 2026-08-29 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-15 | Unit 2 / Phase 1 | Activity 2.3 | Update functional requirement | Thabang Zitha | 2026-08-29 | 2026-08-31 | Completed | 100 | Functional Required SRS | Yes |  | Completed
U2-16 | Unit 2 / Phase 1 | Activity 2.3 | Create requirement change log | Thabang Zitha | 2026-08-29 | 2026-08-31 | Completed | 100 | Unit 2 documentation | Yes |  | Completed
U2-17 | Unit 2 / Phase 1 | Activity 2.3 | update database schema | Nyakallo Pali | 2026-08-29 | 2026-08-31 | Completed | 100 | Updated database schema with payment method, cancelled at and cancellation reason | Yes |  | Completed
U2-18 | Unit 2 / Phase 1 | Activity 2.3 | update SRS with Unit 2 work | All members | 2026-08-29 | 2026-08-31 | Completed | 100 | Finalised SRS | Yes |  | Completed
U2-19 | Unit 2 / Phase 1 | Activity 2.3 | Update Microsoft Project schedule | Yamkela Mazamane | 2026-08-29 | 2026-08-31 | Completed | 100 | Microsoft Project .mpp file | Yes |  | Completed
U2-20 | Unit 2 / Phase 1 | Activity 2.3 | Update GitHub repository | Yamkela Mazamane | 2026-08-30 | 2026-09-02 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U2-21 | Unit 2 / Phase 1 | Activity 2.3 | Update Project Progress Tracker | Yamkela Mazamane | 2026-08-31 | 2026-08-31 | Completed | 100 | Project progress tracker | Yes |  | Completed
U2-22 | Unit 2 / Phase 1 | Activity 2.3 | Confirm important changes with stakeholder | Goitsoene Kgwele | 2026-08-28 | 2026-09-02 | Completed | 100 | Meeting notes to be recorded | Yes |  | Completed
U2-23 | Unit 2 / Phase 1 | Activity 2.3 | Complete Phase 1 group reflection | All members | 2026-08-30 | 2026-08-31 | Completed | 100 | Project progress tracker | Yes |  | Completed
U2-24 | Unit 2 / Phase 1 |  | Powerpoint presentation | All members | 2026-08-30 | 2026-08-31 | Completed | 100 | Phase 1 PowerPoint Presentation | Yes |  | Completed
U3-01 | Unit 3 / Phase 2 | Activity 3.1 | Identify main system components (Flutter, ASP.NET, Supabase) | Nyakallo Pali | 2026-09-01 | 2026-09-03 | Completed | 100 | System Architecture Diagram | Yes |  | Completed
U3-02 | Unit 3 / Phase 2 | Activity 3.1 | Identify who uses each application (user roles) | Goitsoene Kgwele | 2026-09-01 | 2026-09-03 | Completed | 100 | System Architecture Diagram | Yes |  | Completed
U3-03 | Unit 3 / Phase 2 | Activity 3.1 | Define responsibilities of each component | Nyakallo Pali, Bennet Linda | 2026-09-02 | 2026-09-04 | Completed | 100 | System Architecture Diagram explanation | Yes |  | Completed
U3-04 | Unit 3 / Phase 2 | Activity 3.1 | Identify main data flows between components | Nyakallo Pali | 2026-09-02 | 2026-09-04 | Completed | 100 | Data flow table; System Architecture Diagram | Yes |  | Completed
U3-05 | Unit 3 / Phase 2 | Activity 3.1 | Draw System Architecture Diagram | Nyakallo Pali, Bennet Linda | 2026-09-03 | 2026-09-06 | Completed | 100 | System Architecture Diagram | Yes |  | Completed
U3-06 | Unit 3 / Phase 2 | Activity 3.1 | Explain the architecture in writing | Bennet Linda | 2026-09-05 | 2026-09-07 | Completed | 100 | Architecture explanation document | Yes |  | Completed
U3-07 | Unit 3 / Phase 2 | Activity 3.2 | Identify actors from SRS | Thabang Zitha | 2026-09-06 | 2026-09-08 | Completed | 100 | Use Case Diagram; Actor table | Yes |  | Completed
U3-08 | Unit 3 / Phase 2 | Activity 3.2 | Identify use cases for each actor | Thabang Zitha | 2026-09-06 | 2026-09-08 | Completed | 100 | Use Case Diagram; Use case table | Yes |  | Completed
U3-09 | Unit 3 / Phase 2 | Activity 3.2 | Identify use case relationships (include, extend, generalization) | Thabang Zitha | 2026-09-07 | 2026-09-09 | Completed | 100 | Use Case Diagram with relationships | Yes |  | Completed
U3-10 | Unit 3 / Phase 2 | Activity 3.2 | Draw Use Case Diagram with system boundary | Thabang Zitha, Yamkela Mazamane | 2026-09-08 | 2026-09-11 | Completed | 100 | Use Case Diagrams (Customer, Stylist, Manager) | Yes |  | Completed
U3-11 | Unit 3 / Phase 2 | Activity 3.2 | Select important processes for sequence diagrams | Nyakallo Pali, Bennet Linda | 2026-09-09 | 2026-09-10 | Completed | 100 | Process selection document | Yes |  | Completed
U3-12 | Unit 3 / Phase 2 | Activity 3.2 | Draw Sequence Diagram 1: Customer submits appointment request (Flutter - Supabase) | Bennet Linda | 2026-09-10 | 2026-09-13 | Completed | 100 | Sequence Diagram | Yes |  | Completed
U3-13 | Unit 3 / Phase 2 | Activity 3.2 | Draw Sequence Diagram 2: Staff approves appointment (ASP.NET → Supabase) | Nyakallo Pali | 2026-09-10 | 2026-09-13 | Completed | 100 | Sequence Diagram | Yes |  | Completed
U3-14 | Unit 3 / Phase 2 | Activity 3.2 | Draw Sequence Diagram 3: Manager manages services/prices (ASP.NET - Supabase) | Nyakallo Pali | 2026-09-10 | 2026-09-13 | Completed | 100 | Sequence Diagram | Yes |  | Completed
U3-15 | Unit 3 / Phase 2 | Activity 3.2 | Identify entities and attributes for ERD | Nyakallo Pali | 2026-09-12 | 2026-09-14 | Completed | 100 | ERD; Entity attribute table | Yes |  | Completed
U3-16 | Unit 3 / Phase 2 | Activity 3.2 | Identify primary and foreign keys | Nyakallo Pali | 2026-09-13 | 2026-09-15 | Completed | 100 | ERD with PK/FK notation | Yes |  | Completed
U3-17 | Unit 3 / Phase 2 | Activity 3.2 | Draw ERD using diagramming tool | Nyakallo Pali, Yamkela Mazamane | 2026-09-14 | 2026-09-17 | Completed | 100 | ERD with cardinality notation | Yes |  | Completed
U3-18 | Unit 3 / Phase 2 | Activity 3.3 | Review approved requirements and identify required Flutter screens | Bennet Linda | 2026-09-15 | 2026-09-17 | Completed | 100 | Flutter screen list; Requirement-to-interface alignment table | Yes |  | Completed
U3-19 | Unit 3 / Phase 2 | Activity 3.3 | Review approved requirements and identify required ASP.NET pages | Goitsoene Kgwele | 2026-09-15 | 2026-09-17 | Completed | 100 | ASP.NET page list; Requirement-to-interface alignment table | Yes |  | Completed
U3-20 | Unit 3 / Phase 2 | Activity 3.3 | Create Flutter mobile wireframes | Bennet Linda, Yamkela Mazamane | 2026-09-17 | 2026-09-22 | Completed | 100 | Flutter wireframes (Figma) | Yes |  | Completed
U3-21 | Unit 3 / Phase 2 | Activity 3.3 | Create ASP.NET web wireframes | Goitsoene Kgwele, Thabang Zitha | 2026-09-17 | 2026-09-22 | Completed | 100 | ASP.NET wireframes (Figma) | Yes |  | Completed
U3-23 | Unit 3 / Phase 2 | Activity 3.3 | Document navigation flow between screens | Bennet Linda | 2026-09-19 | 2026-09-20 | Completed | 100 | Navigation flow diagram | Yes |  | Completed
U3-24 | Unit 3 / Phase 2 | Activity 3.3 | Check mobile and web integration (Flutter - Supabase - ASP.NET) | Nyakallo Pali | 2026-09-20 | 2026-09-21 | Completed | 100 | Interface-to-ERD alignment table | Yes |  | Completed
U3-25 | Unit 3 / Phase 2 | Activity 3.3 | Check interface information against ERD | Nyakallo Pali, Bennet Linda | 2026-09-20 | 2026-09-21 | Completed | 100 | Design alignment check / traceability matrix | Yes |  | Completed
U3-26 | Unit 3 / Phase 2 | Activity 3.3 | Check alignment across all design artefacts | All members | 2026-09-21 | 2026-09-22 | Completed | 100 | Working prototype (Flutter & ASP.NET); Figma designs | Yes |  | Completed
U3-27 | Unit 3 / Phase 2 | Activity 3.3 | Build initial working prototype (Flutter + ASP.NET + Supabase) | All members | 2026-09-18 | 2026-09-20 | Completed | 100 | Stakeholder feedback record; prototype demo notes | Yes |  | Completed
U3-28 | Unit 3 / Phase 2 | Activity 3.3 | Present working prototype to stakeholder and obtain feedback | All members | 2026-09-20 | 2026-09-20 | Completed | 100 | Updated wireframes and prototype | Yes |  | Completed
U3-29 | Unit 3 / Phase 2 | Activity 3.3 | Update system design and prototype based on stakeholder feedback | All members | 2026-09-21 | 2026-09-22 | Completed | 100 | Updated Microsoft Project | Yes |  | Completed
U3-30 | Unit 3 / Phase 2 | Activity 3.3 | Update Microsoft Project with Phase 2 progress | Yamkela Mazamane | 2026-09-22 | 2026-09-23 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U3-31 | Unit 3 / Phase 2 | Activity 3.3 | Update GitHub with Phase 2 design documentation | Yamkela Mazamane | 2026-09-22 | 2026-09-23 | Completed | 100 | Updated Project Progress Tracker | Yes |  | Completed
U3-32 | Unit 3 / Phase 2 | Activity 3.3 | Update Project Progress Tracker | Yamkela Mazamane | 2026-09-23 | 2026-09-24 | Completed | 100 | Checkpoint readiness checklist | Yes |  | Completed
U3-33 | Unit 3 / Phase 2 | Activity 3.3 | Complete Unit 3 Group Progress Checkpoint | All members | [5 empty] | Yes |  | On Track
U3-34 | Unit 3 / Phase 2 |  | Powerpoint presentation | All members | 2026-10-01 | 2026-10-01
U4-01 | Unit 4 / Phase 3 | Activity 4.1 | Set up and verify development branches, environment configuration, and project dependencie | All members | 2026-10-01 | 2026-10-06 | Completed | 100 | Updated Microsoft Project | Yes |  | Completed
U4-02 | Unit 4 / Phase 3 | Activity 4.1 | Implement Supabase schema, relationships, constraints, test data, and Row Level Security policies | Goitseone Kgwele, Thabang Zitha, Yamkela Mazamani (manager portal); backend shared by team | 2026-10-01 | 2026-10-06 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-03 | Unit 4 / Phase 3 | Activity 4.1 | Implement Flutter customer/stylist screens and navigation using the approved designs | Bennet Linda, Nyakallo Pali | 2026-10-01 | 2026-10-07 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-04 | Unit 4 / Phase 3 | Activity 4.1 | Implement service catalogue, prices, durations, salon details, operating hours, and Cut and Dye promotion | Bennet Linda, Nyakallo Pali | 2026-10-07 | 2026-10-14 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-05 | Unit 4 / Phase 3 | Activity 4.1 | Implement appointment booking with stylist/date/time selection and input validation | Bennet Linda, Nyakallo Pali | 2026-10-09 | 2026-10-21 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-06 | Unit 4 / Phase 3 | Activity 4.1 | Implement booking conflict detection and availability checks to prevent double bookings | Bennet Linda, Nyakallo Pali | 2026-10-10 | 2026-10-22 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-07 | Unit 4 / Phase 3 | Activity 4.1 | Implement customer cancellation and restore the cancelled appointment slot | Bennet Linda, Nyakallo Pali | 2026-10-11 | 2026-10-23 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-08 | Unit 4 / Phase 3 | Activity 4.1 | Implement cash/card-on-arrival payment preference and display it in booking details | Bennet Linda, Nyakallo Pali | 2026-10-12 | 2026-10-24 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-09 | Unit 4 / Phase 3 | Activity 4.1 | Implement ASP.NET manager authentication and secure access to the manager portal | Goitseone Kgwele, Thabang Zitha, Yamkela Mazamani | 2026-10-13 | 2026-10-25 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-10 | Unit 4 / Phase 3 | Activity 4.1 | Implement manager booking dashboard and create, view, update, cancel booking workflows | Goitseone Kgwele, Thabang Zitha, Yamkela Mazamani | 2026-10-14 | 2026-10-26 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-11 | Unit 4 / Phase 3 | Activity 4.1 | Implement stylist, service, schedule, and promotion management features within agreed scope | Goitseone Kgwele, Thabang Zitha, Yamkela Mazamani | 2026-10-15 | 2026-10-27 | Completed | 100 | Github commit | Yes |  | Completed
U4-12 | Unit 4 / Phase 3 | Activity 4.2 | Connect Flutter, ASP.NET Core, and Supabase; verify shared data and update flows | All members (Flutter: Bennet & Nyakallo; ASP.NET: Goitseone, Thabang & Yamkela) | 2026-10-16 | 2026-10-28 | Completed | 100 | Supabase Project Setup | Yes |  | Completed
U4-13 | Unit 4 / Phase 3 | Activity 4.2 | Perform and document initial function checks against the Unit 4 SRS (not a formal testing cycle) | All members | 2026-10-17 | 2026-10-29 | Completed | 100 | Supabase Project Setup | Unit 4 SRS, pp. 6–13: initial function/integration checks |  | Completed
U4-14 | Unit 4 / Phase 3 | Activity 4.2 | Check authentication, permissions, forms and shared data at prototype demonstration level | All members | 2026-10-18 | 2026-10-30 | Completed | 100 | test results | Unit 4 SRS, pp. 6–13: initial function/integration checks |  | Completed
U4-15 | Unit 4 / Phase 3 | Activity 4.2 | Correct documented integration issues; complete formal regression review before final submission | All members | 2026-10-19 | 2026-10-31 | Completed | 75 | Unit 4 SRS p.11–12: integration corrections; formal regression not evidenced | Yes | In Progress | Completed
U4-16 | Unit 4 / Phase 3 | Activity 4.3 | Update SRS and technical documentation; prepare setup instructions, test evidence, screenshots, and user guidance | Goitseone Kgwele, Thabang Zitha, Yamkela Mazamani (documentation); Bennet & Nyakallo (mobile screenshots) | 2026-10-20 | 2026-11-01 | Completed | 100 | Updated Project Progress Tracker | Yes |  | Completed
U4-17 | Unit 4 / Phase 3 | Activity 4.3 | Update GitHub, Microsoft Project, task tracker, contribution records, and final submission checklist | All members; Yamkela and Goitseone coordinate project records | 2026-10-21 | 2026-11-02 | Completed | 100 | Updated Project Progress Tracker | Yes |  | Completed
U4-18 | Unit 4 / Phase 3 | Activity 4.3 | Verify final integrated Flutter + Supabase + ASP.NET deliverable and submit all working files/documentation | All members | 2026-10-22 | 2026-11-03 | Completed | 100 | https://github.com/Yamkela47/Group-B-.git | Yes |  | Completed
U4-19 | Unit 4 / Phase 3 |  | Prepare presentation slides, demo script, backup screenshots/video, and rehearse demonstration | All members | 2026-10-23 | 2026-11-04 | Completed | 100 |  | Yes |  | Completed
U4-20 | Unit 4 / Phase 3 |  | Presentation | All members | 2026-10-24 | 2026-10-30 | Completed | 100 |  | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Goitsoene Kgwele | 221050663 | Unit 1 / Phase 1 | Activity 1.1 | Stakeholder identification and confirmation | Identified and confirmed Cutting Edge Salon as the external stakeholder. Arranged and coordinated the initial stakeholder meeting. | 2026-08-18 | 3 | SRS - Stakeholders and User Groups, Interview photos | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview preparation and conduct | Prepared interview questions. Led the stakeholder interview session. Documented key findings and requirements. | 2026-08-18 | 4 | Interview Questions and Responses, Photos | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | SRS coordination | Coordinated the compilation of the initial SRS document. Ensured all 17 sections were completed. Integrated team contributions. | 2026-08-25 | 6 | Initial SRS Document | Yes | 25/08/2026
|  | Unit 2 / Phase 1 | Activity 2.1 | Ethical feasibility evaluation | Evaluated ethical feasibility. Assessed stakeholder informed consent, data collection necessity, and customer empowerment features. | 2026-08-28 | 2 | Unit 2 documentation | Yes | 29/08/2026
|  | Unit 2 / Phase 1 | Activity 2.2 | Risk register oversight | Oversaw the creation of the risk register. Prepared risk register format. Reviewed all 10 risks for completeness. | 2026-08-29 | 3 | Unit 2 documentation - Risk Registe | Yes | 2026-08-31
|  | Unit 2 / Phase 1 | Activity 2.2 | Phase 1 group reflection coordination | Coordinated and documented the Phase 1 group reflection. Compiled responses from all members. | 2026-08-31 | 2 | Unit 2 documentation - Phase 1 Group Reflection | Yes | 31/08/2026
|  | Unit 2 / Phase 1 | Additional | GenAI course participation | Actively participated in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 31/08/2026 | 4 members enrolled
|  | Unit 3 / Phase 2 | Activity 3.1 | User roles identification | Identified all system users and roles (Customer, Stylist, Manager). Documented who uses Flutter vs ASP.NET and their main purposes. | 2026-09-03 | 2 | System Architecture Diagram | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | ASP.NET page identification | (Login, Dashboard, Bookings, Stylists, Services & Promotions, Schedule, Reports, Gallery, My Profile) | 2026-09-17 | 2 | ASP.NET page list; Requirement-to-interface alignment table | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | ASP.NET wireframe creation | Created ASP.NET web wireframes using Figma for all main pages. Focused on layout, navigation, labels, input fields, buttons, tables, and user actions. | 2026-09-20 | 6 | ASP.NET wireframes (Figma) | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Stakeholder feedback | Organised and conducted stakeholder feedback session. Presented designs and gathered feedback. Documented comments and changes requested. | 2026-09-20 | 3 | Stakeholder feedback record | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Checkpoint | Unit 3 Group Progress Checkpoint | Reviewed all Phase 2 artefacts against checkpoint requirements. Confirmed completeness of architecture, UML, ERD, and interface designs. | 2026-09-25 | 2 | Checkpoint readiness checklist | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Additional | GenAI course participation | Continued participation in GenAI | Ongoing | 4 | GenAI course attendance records | Yes | 2026-09-25
|  | Unit 4 / Phase 3 | Activity 4.3 | ASP.NET Manager Portal; coordination | Worked within the ASP.NET manager portal team (with Thabang and Yamkela), contributed to project coordination and final SRS/tracker review. Exact personal commits and hours require confirmation. | 2026-10-24 | 40 | Project Progress Tracker; GitHub repository https://github.com/Yamkela47/Group-B-.git | Yes | 2026-10-25
Thabang Zitha | 223007074 | Unit 1 / Phase 1 | Activity 1.1 | Current process and problem documentation | Documented the current manual process. Created process flow diagram. Wrote the problem statement. | 2026-08-20 | 4 | SRS: Current Process and Diagram | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.1 | Project aim, objectives and scope definition | Defined project aim, 8 objectives, and project scope including deliverables, acceptance criteria, exclusions, constraints, and assumptions. | 2026-08-20 | 3 | SRS - Purpose, Aim and Objectives, Project Scope | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview preparation | Prepared interview questions for stakeholder. Ensured all key areas were covered. | 2026-08-17 | 2 | Interview Questions and Responses | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | Functional requirements documentation | Documented 17 functional requirements. Created requirements prioritisation using MoSCoW method. | 2026-08-24 | 4 | SRS : Functional Requirements, MoSCoW | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | Non-functional requirements documentation | Documented 8 non-functional requirements covering usability, performance, security, availability, and quality. | 2026-08-24 | 2 | SRS: Non-Functional Requirements | Yes | 25/08/2026
|  | Unit 2 / Phase 1 | Activity 2.1 | Legal feasibility evaluation | Evaluated legal feasibility. Assessed data protection, privacy, personal information collection, and GitHub security measures. | 2026-08-28 | 2 | Unit 2 documentation | Yes | 29/08/2026
|  | Unit 2 / Phase 1 | Activity 2.3 | Refine project scope | Refined project scope based on feasibility findings. Documented decisions for each function (Keep, Simplify, Postpone, Remove). | 2026-08-30 | 3 | Unit 2 documentation - Refined Project Scope | Yes | 31/08/2026
|  | Unit 2 / Phase 1 | Activity 2.3 | Update functional requirements (FR-08, FR-18) | Added FR-08 (Customer Cancellation) and FR-18 (Payment Method Selection) as Must Have requirements based on lecturer feedback. Updated MoSCoW prioritisation. | 2026-08-31 | 3 | SRS: Functional Requirements, MoSCoW | Yes | 31/08/2026
|  | Unit 2 / Phase 1 | Activity 2.3 | Create requirements change log | Created comprehensive requirements change log documenting all changes including FR-08 (changed to Must Have), FR-18 (new), FR-09 (simplified), FR-13 (postponed). | 2026-08-31 | 2 | Unit 2 documentation - Requirements Change Lo | Yes | 31/08/2026
|  | Unit 2 / Phase 1 | Additional | GenAI course participation | Actively participated in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 31/08/2026 | 4 members enrolled
|  | Unit 3 / Phase 2 | Activity 3.2 | Actor identification | Identified all actors from SRS (Customer, Stylist, Manager). Documented what each actor needs to do. | 2026-09-08 | 2 | Use Case Diagram; Actor table | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | Use case identification | Identified use cases for each actor using clear verb + object names. Created use case table mapping actors to possible use cases. | 2026-09-08 | 3 | Use Case Diagram; Use case table | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | Use case relationships | Identified appropriate <<include>>, <<extend>> and generalization relationships. Justified each relationship based on system logic. | 2026-09-09 | 3 | Use Case Diagram with relationships | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | Use Case Diagram creation | Drew complete Use Case Diagrams with system boundary | 2026-09-11 | 4 | Use Case Diagrams (Customer, Stylist, Manager) | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | ASP.NET wireframe creation | Created ASP.NET web wireframes using Figma. Focused on layout, navigation, labels, input fields, buttons, tables, and user actions. | 2026-09-20 | 5 | ASP.NET wireframes (Figma) | Yes | 2026-09-25
|  | Unit 4 / Phase 3 | Activity 4.1 / 4.3 | ASP.NET Manager Portal development | Worked with Goitseone and Yamkela on the ASP.NET Manager Portal, including manager-side booking, service and stylist workflows as described in the Unit 4 SRS. Verify individual code contributions. | 2026-10-24 | 40 | GitHub repository https://github.com/Yamkela47/Group-B-.git; Unit 4 SRS | Yes | 2026-10-21
|  | Unit 3 / Phase 2 | Additional | GenAI course participation | Continued participation in GenAI course for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 2026-09-25
Nyakallo Pali | 223060226 | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview participation | Participated in the stakeholder interview. Took notes on technical requirements and backend preferences. | 2026-08-18 | 2 | Interview Questions and Responses | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | Initial SRS - Backend and integration sections | Contributed to SRS sections including System Requirements, Integration Requirements, and Main ASP.NET and Supabase Functions. | 2026-08-25 | 4 | SRS - System Requirements,: Integration Requirements, Main Functions | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | Supabase project setup | Created the initial Supabase project for Cutting Edge SMS. Configured database tables for Users, Bookings, Services, and Stylists. | 2026-08-25 | 3 | Supabase Project Setup Screenshot | Yes | 25/08/2026
|  | Unit 2 / Phase 1 | Activity 2.1 | Technical feasibility evaluation | Led the technical feasibility evaluation. Assessed Flutter, ASP.NET, and Supabase skills. Identified technical strengths and limitations. Determined GenAI course participation benefits. | 2026-08-28 | 4 | Unit 2 documentation - Technical Feasibility | Yes | 29/08/2026
|  | Unit 2 / Phase 1 | Activity 2.2 | Risk identification (R01, R04, R06) | Identified and documented technical risks: R01 (Supabase integration), R04 (integration delays), R06 (email system failure). Provided mitigation and contingency actions. | 2026-08-29 | 3 | Unit 2 documentation - Risk Register | Yes | 29/08/2026
|  | Unit 2 / Phase 1 | Activity 2.3 | Update database schema | Designed and documented database schema updates including payment_method (VARCHAR 10), cancelled_at (TIMESTAMP), and cancellation_reason (VARCHAR 255) fields for the Bookings table. | 2026-08-31 | 3 | Unit 2 documentation - Database Schema Update | Yes | 31/08/2026
|  | Unit 2 / Phase 1 | Activity 2.3 | SRS update - Feasibility section | Integrated the complete feasibility study into the SRS document. Ensured all 6 feasibility areas were properly documented. | 2026-08-31 | 3 | Updated SRS - Feasibility Study | Yes | 31/08/2026
|  | Unit 2 / Phase 1 | Additional | GenAI course participation | Actively participated in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 31/08/2026 | 4 members enrolled
|  | Unit 3 / Phase 2 | Activity 3.1 | System components identification | Identified main system components (Flutter, ASP.NET, Supabase Auth, Supabase Database, Supabase Storage). | 2026-09-03 | 2 | System Architecture Diagram | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.1 | Component responsibilities | Defined responsibilities of each component (Flutter, ASP.NET, Supabase). Explained what each component is responsible for. | 2026-09-04 | 2 | System Architecture Diagram explanation | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.1 | Data flow identification | Identified main data flows between components. Documented information exchanged between Flutter, ASP.NET and Supabase. | 2026-09-04 | 2 | Data flow table; System Architecture Diagram | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.1 | System Architecture Diagram | Drew complete System Architecture Diagram showing all components, connections, data flows and direction. | 2026-09-06 | 4 | System Architecture Diagram (Lucidchart/Figma) | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | Sequence Diagram (Stylist Flutter process) | Drew Sequence Diagram for Staff approves appointment: Staff ASP.NET Supabase. Included actor, lifelines, messages, requests, responses, activation and correct order. | 2026-09-13 | 4 | Sequence Diagram | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | Entity identification | (profiles, stylists, stylist_schedules, bookings, services, promotions, cancellations, payment_methods, gallery_images) | 2026-09-14 | 3 | ERD; Entity attribute table | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | Primary and foreign keys | Identified primary and foreign keys for all entities. Documented key relationships. | 2026-09-15 | 2 | ERD with PK/FK notation | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | Relationships and cardinality | Identified relationships and cardinality between entities. Documented one-to-many and many-to-many relationships. | 2026-09-15 | 2 | ERD with cardinality notation | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | ERD creation | Drew complete ERD using diagramming tool. Included all entities, attributes, keys, relationships and cardinality. | 2026-09-17 | 4 | ERD | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Integration check | Checked mobile and web integration (Flutter - Supabase - ASP.NET). Verified data flows and shared backend usage. | 2026-09-21 | 2 | Integration check table | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Interface-to-ERD alignment | Checked that all interface information is supported by ERD. Created alignment table. | 2026-09-21 | 2 | Interface-to-ERD alignment table | Yes | 2026-09-25
|  | Unit 4 / Phase 3 | Activity 4.1 / 4.2 | Flutter Customer/Stylist app and shared Supabase integration | Worked with Bennet on Flutter Customer/Stylist screens and shared Supabase integration, including booking and availability flows. Individual commits should be reconciled. | 2026-10-24 |  | GitHub repository https://github.com/Yamkela47/Group-B-.git; Supabase evidence; Unit 4 SRS | Yes | 2026-10-25
|  | Unit 3 / Phase 2 | Additional | GenAI course participation | Continued participation in GenAI course for Supabase and ASP.NET skill enhancement. Applied learning to architecture and ERD design. | Ongoing | 4 | GenAI course attendance records | Yes | 2026-09-25
Bennet Linda | 224004294 | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview participation | Participated in the stakeholder interview. Took notes on frontend requirements, UI preferences, and "Luxury" brand expectations. | 2026-08-18 | 2 | Interview Questions and Responses | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | Initial SRS - Frontend and UI sections | Contributed to SRS sections including Product Perspective, Main Flutter Functions, and User Interface requirements. | 2026-08-25 | 4 | SRS - Product Perspective, : Main Functions | Yes | 25/08/2026
|  | Unit 2 / Phase 1 | Activity 2.1 | Operational feasibility evaluation | Led the operational feasibility evaluation. Assessed whether the proposed solution works for the stakeholder and intended users. Evaluated suitability for target users (ages 10-30). | 2026-08-28 | 4 | Unit 2 documentation, Operational Feasibility | Yes | 29/08/2026
|  | Unit 2 / Phase 1 | Activity 2.2 | Risk identification (R04, R07) | Identified and documented technical risks: R04 (integration between Flutter, ASP.NET, and Supabase) and R07 (Google Maps API quota limitations). | 2026-08-29 | 2 | Unit 2 documentation - Risk Register | Yes | 29/08/2026
|  | Unit 2 / Phase 1 | Activity 2.3 | SRS update - Refined project scope | Documented the refined project scope with decisions for each function: Keep (14 requirements), Simplify (FR-09), Postpone (FR-13). | 2026-08-31 | 3 | Unit 2 documentation - Refined Project Scope | Yes | 31/08/2026
|  | Unit 3 / Phase 2 | Activity 3.1 | Component responsibilities | Defined responsibilities of Flutter and ASP.NET components. Explained integration with Supabase. | 2026-09-04 | 2 | System Architecture Diagram explanation | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.1 | System Architecture Diagram | Co-drew System Architecture Diagram. Ensured Flutter, ASP.NET and Supabase shown as one integrated system. | 2026-09-06 | 3 | System Architecture Diagram | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.1 | Architecture explanation | Wrote detailed explanation of architecture: who uses Flutter, who uses ASP.NET, Supabase responsibilities, communication methods, integration. | 2026-09-07 | 2 | Architecture explanation document | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | Process selection | Selected important processes for sequence diagrams. Ensured one Flutter process and one ASP.NET process. | 2026-09-10 | 2 | Process selection document | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | Sequence Diagram | Drew Sequence Diagram for Customer submits appointment request: Customer - Flutter Supabase. Included actor, lifelines, messages, requests, responses, activation and correct order | 2026-09-13 | 4 | Sequence Diagram | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Flutter screen identification | Reviewed approved requirements and identified required Flutter screens (Login, Register, Home, Request Appointment, My Appointments, Profile). Mapped each screen to related requirements/use cases. | 2026-09-17 | 2 | Flutter screen list; Requirement-to-interface alignment table | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Flutter wireframe creation | Created Flutter mobile wireframes using Figma for all main screens. Focused on layout, navigation, labels, input fields, buttons, and user actions. | 2026-09-20 | 6 | Flutter wireframes (Figma) | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Navigation flow | Documented navigation flow between screens. Created navigation flow diagram showing how users move through the application. | 2026-09-20 | 3 | Navigation flow diagram | Yes | 2026-09-25
|  | Unit 4 / Phase 3 | Activity 4.1 / 4.2 | Flutter Customer/Stylist application | Worked with Nyakallo on Flutter customer/stylist views, booking, cancellation, payment preference and stylist schedule screens documented in Unit 4. Verify personally completed portions. | 2026-10-24 | 40 | GitHub repository https://github.com/Yamkela47/Group-B-.git; Flutter screenshots; Unit 4 SRS | Yes | 2026-10-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Interface-to-ERD alignment | Checked that all interface information is supported by ERD. Created alignment table. | 2026-09-21 | 2 | Interface-to-ERD alignment table | Yes | 2026-09-25
Yamkela Mazamani | 224007421 | Unit 1 / Phase 1 | Activity 1.2 | Stakeholder interview participation | Participated in the stakeholder interview. Documented interview findings and organised stakeholder evidence. | 2026-08-18 | 2 | Interview Questions and Responses, Photos | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | Microsoft Project schedule creation | Created the initial Microsoft Project schedule with tasks, dates, durations, responsibilities, dependencies, and milestones. | 2026-08-25 | 4 | Microsoft Project .mpp file | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | GitHub repository creation | Created and configured the GitHub repository. Set up folder structure. Added README and initial documentation | 2026-08-23 | 3 | https://github.com/Yamkela47/Group-B-.git | Yes | 25/08/2026
|  | Unit 1 / Phase 1 | Activity 1.3 | Progress report and contribution record | Completed the progress report and contribution record for Unit 1. Documented all team contributions. | 2026-08-25 | 2 | Project Progress Tracker - Unit 1 | Yes | 25/08/2026
|  | Unit 2 / Phase 1 | Activity 2.1 | Schedule feasibility evaluation | Evaluated schedule feasibility. Assessed whether all work can be completed within the semester. Identified time constraints and required changes. | 2026-08-28 | 3 | Unit 2 documentation - Schedule Feasibility | Yes | 29/08/2026
|  | Unit 2 / Phase 1 | Activity 2.2 | Risk register formatting | Formatted the risk register. Created the risk register table with all 10 risks, likelihood, impact, scores, mitigation, contingency, owners, and status. | 2026-08-29 | 3 | Unit 2 documentation - Risk Register | Yes | 29/08/2026
|  | Unit 2 / Phase 1 | Activity 2.3 | Microsoft Project schedule update | Updated the Microsoft Project schedule to reflect Unit 2 progress and refined scope. Added new tasks for FR-08 and FR-18 implementation. | 2026-08-31 | 4 | Updated Microsoft Project .mpp file | Yes | 31/08/2026
|  | Unit 2 / Phase 1 | Activity 2.3 | GitHub repository maintenance | Maintained the GitHub repository. Added Unit 2 documentation, feasibility study, risk register, and updated SRS. | 2026-08-31 | 3 | https://github.com/Yamkela47/Group-B-.git | Yes | 31/08/2026
|  | Unit 2 / Phase 1 | Activity 2.3 | Project Progress Tracker update | Updated the Project Progress Tracker for Unit 2. Recorded task progress, individual contributions, challenges, and actions. | 2026-08-31 | 3 | Updated Project Progress Tracker | Yes | 31/08/2026
|  | Unit 2 / Phase 1 | Additional | GenAI course participation | Actively participated in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 31/08/2026 | 4 members enrolled
|  | Unit 3 / Phase 2 | Activity 3.2 | Use Case Diagram support | Supported creation of Use Case Diagrams. | 2026-09-11 | 3 | Use Case Diagram | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.2 | ERD support | Supported creation of ERD. Ensured proper notation for entities, attributes, keys, relationships and cardinality. | 2026-09-17 | 3 | ERD | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Flutter wireframe creation | Created Flutter mobile wireframes using Figma. Focused on layout, navigation, labels, input fields, buttons, and user actions. | 2026-09-20 | 5 | Flutter wireframes | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Microsoft Project update | Updated Microsoft Project schedule with Phase 2 tasks, progress and upcoming development activities. | 2026-09-23 | 3 | Updated Microsoft Project | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | GitHub maintenance | Updated GitHub repository with all Phase 2 design documentation (architecture, UML, ERD, wireframes) | 2026-09-23 | 3 | https://github.com/Yamkela47/Group-B-.git | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Activity 3.3 | Project Progress Tracker update | Updated Project Progress Tracker for Phase 2. Recorded task progress, individual contributions, challenges, and actions. | 2026-09-23 | 3 | Updated Project Progress Tracker | Yes | 2026-09-25
|  | Unit 3 / Phase 2 | Additional | GenAI course participation | Continued participation in GenAI course for Supabase and ASP.NET skill enhancement. | Ongoing | 4 | GenAI course attendance records | Yes | 2026-09-25
|  | Unit 4 / Phase 3 | Activity 4.3 | ASP.NET Manager Portal and documentation | Worked with Goitseone and Thabang on the ASP.NET manager portal; supported documentation and project records. Confirm exact individual activities and evidence. | 2026-10-25 | 6 | Updated Unit 4 SRS; Project Progress Tracker; GitHub repository https://github.com/Yamkela47/Group-B-.git | Yes | 2026-10-25

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-18 | Unit 1 / Phase 1 | Meeting | Conduct initial stakeholder interview to identify the problem, gather requirements, understand current process, and confirm stakeholder needs and expectations. | All members | Cutting Edge Salon Owner / Manager | • Salon Name: Cutting Edge • Established: 11 April 2022 • Main Problem: "To alleviate mismanagement of daily store running" • Main Goals: "To showcase our products and services and to allow for a smooth booking system" • Target Audience: 10-30 years old, everyone (Men, Women, Children) • Core Services: Hair cutting, hair colouring, beard shaving, hot towel treatment • Brand Vibe: "Luxury" • Competitor: Legendary Barber • Desired Pages: Home, About Us, Services, Pricing, Our Team, Gallery, Booking • Operating Hours: Weekdays 9-6, Saturdays 8:30-5, Sundays 08:30-13:00 • Address: 10 Melck Street, Pioneer Building, Welkom Central • Contact: 0787676599 / cutinged@88@gmail.com • Stylists: All offer the same services • WhatsApp for Bookings: NO (confirmed) • Services: Standard haircut = 40 min, Cut & Dye = 1h 15min | Document all findings in SRS. Begin development of Initial Software Requirements Specification (SRS). | Interview Questions and Responses (Full Transcript) Interview Meeting Evidence (Photos) Interview notes, meeting records
2026-08-18 | Unit 1 / Phase 1 | Requirements confirmation | Summarise main findings and confirm that the group's understanding of the stakeholder's needs and requirements is correct. | All members | Cutting Edge Salon Owner / Manager | Confirmed Findings: • The current manual diary system is inefficient and causes mismanagement • The stakeholder wants customers to book online • The stakeholder wants a "Luxury" feel • The stakeholder does NOT want WhatsApp bookings • The stakeholder has stylists who all offer the same services • The stakeholder wants pages: Home, About Us, Services, Pricing, Our Team, Gallery, Booking • Promote "Cut and Dye" as the flagship service | Proceed with SRS development based on confirmed requirements. | Appendix C: Stakeholder Confirmation of Findings Summary notes
31 Aug - 2 Sep 2026 | Unit 2 / Phase 1 | Scope change discussion | Present and discuss lecturer-advised scope changes and new requirements: FR-08 (Customer Cancellation) and FR-18 (Payment Method Selection - Cash/Card). | Goitseone Kgwele, Thabang Zitha | Cutting Edge Salon Owner / Manager | Pending confirmation Proposed Changes to Discuss: • FR-08: Customer cancellation functionality (lecturer-advised) • FR-18: Payment method selection (cash or card) - lecturer-advised • FR-09: Email reminders simplified to manual reminders • FR-13: Gallery display postponed to Phase 2 • Scope refinement based on feasibility study findings Reasons: Lecturer feedback; ensures comprehensive functionality; improves customer experience and staff efficiency | Record stakeholder comments. Confirm acceptance of changes. Update SRS accordingly. Document meeting notes and confirmation. | Meeting notes to be recorded Email confirmation or WhatsApp communication
2026-09-02 | Unit 2 / Phase 1 | Final scope confirmation | Confirm all scope changes and refined project scope with stakeholder. Obtain final approval. | Goitseone Kgwele, Thabang Zitha | Cutting Edge Salon Owner / Manager | Pending confirmation Final Scope to Confirm: • 14 Must Have requirements including FR-08 and FR-18 • 4 Should Have requirements • FR-13 (Gallery) postponed to Phase 2 • FR-09 (Email reminders) simplified to manual reminders • Database schema updates: payment_method, cancelled_at, cancellation_reason • Refined project scope and deliverables | Obtain stakeholder confirmation. Document final decisions. Update SRS with confirmed changes. | Confirmation summary Signed confirmation (if available) Email or WhatsApp communication
2026-09-20 |  |  | Present the working prototype (Flutter & ASP.NET) to the stakeholder for feedback and approval | Thabang Zitha & Nyakallo Pali | Cutting Edge Salon Manager | Stakeholder reviewed the complete Figma interface designs. Approved the Flutter Customer and Stylist interfaces and the ASP.NET Manager Portal. Praised the "luxury" gold/black aesthetic and clean layout. Requested that the "Cut and Dye" service be prominently displayed on the Customer Home screen. Asked that the booking confirmation clearly show the selected payment method (Cash/Card on arrival). Confirmed the cancellation flow is simple and clear. Asked that the gallery be prominent in the Manager Portal. | Keep cancellation flow simple. Emphasise gallery in Manager Portal. Apply changes and document. | A picture of the stakeholder viewing the prototype
2026-10-01 - 2026-10-21 | Unit 4 / Phase 3 | Implementation alignment / prior feedback review | Check implementation against the stakeholder requirements and feedback already documented in the SRS. The Unit 4 SRS does not record a new Phase 3 stakeholder meeting. | Development group | Cutting Edge Salon Owner / Manager (previously consulted; no new meeting recorded) | Implementation was guided by the previously confirmed requirements: luxury black-and-gold design, online booking, cash/card preference, simple cancellation, Cut and Dye promotion and manager oversight. Do not treat this entry as a new stakeholder approval. | If a Phase 3 review occurred, add its actual date, attendees, feedback, decisions and evidence link. Otherwise retain the earlier 20 September 2026 engagement as the latest documented stakeholder feedback. | Unit 4 SRS; prior stakeholder feedback record dated 2026-09-20. No new Phase 3 meeting evidence included.

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-18 | Unit 1 / Phase 1 | Coordinating schedules for the in-person stakeholder interview due to conflicting availability of all group members and stakeholder. | Delayed the stakeholder interview by 2 days. Affected the start of requirements documentation. | Rescheduled interview to a mutually convenient date. Communicated with stakeholder via multiple channels (call, WhatsApp, email) to confirm availability. Assigned Goitseone as primary contact. | Goitseone Kgwele | 2026-08-18 | Resolved
2026-08-18 | Unit 1 / Phase 1 | Translating subjective stakeholder requirements (e.g., "Luxury" feel) into measurable non-functional requirements. | Potential ambiguity in requirements could lead to misinterpretation during development. | Conducted detailed follow-up questions during interview. Documented specific UI/UX expectations (e.g., elegant colour scheme, premium feel, smooth animations). Referenced brand colours and materials provided by stakeholder. | Thabang Zitha | 2026-08-20 | Resolved
2026-08-25 | Unit 2 / Phase 1 | Supabase integration confidence - the group has practical experience but recognises the need for enhanced skills. | Could delay backend integration and database operations during development phase. | Four members enrolled in the GenAI course conducted by Ms Lonergan for Supabase and ASP.NET skill enhancement. Shared learning across the entire group. Created plan to test basic integration early. | Nyakallo Pali | Ongoing | Resolved
2026-08-26 | Unit 2 / Phase 1 | Managing the expanded scope of 19 functional requirements (17 original + 2 new additions). | Risk of scope creep; could prevent prototype completion within the semester. | Conducted MoSCoW prioritisation analysis. Identified 14 Must Have requirements (including FR-08 and FR-18) and 4 Should Have requirements. Postponed FR-13 (Gallery) to Phase 2. Simplified FR-09 (Email reminders) to manual reminders. | Thabang Zitha | 2026-08-31 | Resolved
2026-08-27 | Unit 2 / Phase 1 | Incorporating lecturer feedback (FR-08: Customer Cancellation, FR-18: Payment Method Selection) requiring updates to SRS, database schema, and process flows. | Required significant updates to existing documentation. Potential schedule impact. | Added FR-08 and FR-18 as Must Have requirements. Updated SRS Updated database schema with paymentmethod, cancelledat, and cancellation reason fields. Created requirements change log. | Thabang Zitha, Nyakallo Pali | 2026-08-31 | Resolved
2026-08-27 | Unit 2 / Phase 1 | One group member (Yamkela Mazamani) not enrolled in the GenAI course for Supabase enhancement. | Knowledge gap may affect Supabase integration contributions from that member. | Group agreed to share all GenAI learnings with non-enrolled member. Scheduled knowledge transfer sessions during weekly meetings. All group members committed to supporting each other. | All Members | Ongoing | Resolved
2026-08-28 | Unit 2 / Phase 1 | Risk of unequal participation and poor communication affecting project progress and quality. | Could cause delays, incomplete tasks, and reduced quality of deliverables. | Established weekly group progress meetings (every Monday). Record tasks and contributions in Project Progress Tracker. Maintain daily WhatsApp group for communication. Assigned clear tasks with deadlines. Escalation process established if concerns arise. | Goitseone Kgwele | 2026-08-31 | Resolved
2026-08-29 | Unit 2 / Phase 1 | Limited time available for testing and corrections in the development schedule. | Could affect prototype quality and stakeholder acceptance. | Allocated dedicated testing time in Microsoft Project schedule (1.5 weeks). Developed test cases early. Prioritised critical functionality testing. Simplified features where necessary to reduce testing burden. | Yamkela Mazamani | 2026-08-31 | Resolved
2026-08-31 | Unit 2 / Phase 1 | Stakeholder confirmation of scope changes still pending. | Cannot finalise SRS until stakeholder approves new features and scope changes. | Scheduled meeting with stakeholder for 31 Aug - 2 Sep 2026. Prepared presentation of changes and reasons (lecturer feedback, feasibility findings). Will document stakeholder response and update SRS accordingly. | Goitseone Kgwele | 2026-09-02 | Resolved
2026-08-31 | Unit 2 / Phase 1 | Balancing stakeholder expectations with realistic deliverables based on feasibility findings. | Risk of stakeholder dissatisfaction if features are postponed or removed. | Prepared clear rationale for all scope changes based on feasibility study findings. Will present benefits of core functionality first. Emphasised that postponed features (FR-13) can be added later. | Thabang Zitha | 2026-09-02 | Resolved
2026-09-05 | Unit 3 / Phase 2 | Ensuring alignment across all design artefacts (SRS, Architecture, Use Case, Sequence, ERD, Interfaces) for 19 functional requirements. | Risk of inconsistencies between diagrams and requirements. Potential confusion during development. | Created design alignment check tables. Cross-referenced each requirement across all artefacts. Held group review sessions to verify alignment. | Thabang Zitha, Nyakallo Pali | 2026-09-22 | Resolved
2026-09-10 | Unit 3 / Phase 2 | Designing the database schema to support payment method tracking and cancellation workflow required careful planning. | Potential for incomplete data model. Risk of rework during development. | Updated ERD with payment_methods entity and cancellations table. Verified against sequence diagrams and interface requirements. | Nyakallo Pali | 2026-09-17 | Resolved
2026-09-11 | Unit 3 / Phase 2 | Creating wireframes that reflect the "luxury" aesthetic while remaining functional for required iterative design. | Potential mismatch between stakeholder expectations and usability. | Conducted design reviews. Referenced stakeholder brand colours (gold/black) and materials. Iterated on wireframes based on group feedback. Ensured clean, elegant layout. | Bennet Linda, Yamkela Mazamane | 2026-09-20 | Resolved
2026-09-12 | Unit 3 / Phase 2 | Coordinating group availability for design reviews and stakeholder feedback sessions. | Slight delays in finalising designs | Scheduled reviews in advance. Used WhatsApp for asynchronous feedback. Assigned clear deadlines for each design artefact. | Goitsoene Kgwele | 2026-09-20 | Resolved
2026-09-14 | Unit 3 / Phase 2 | Managing the scope of 19 functional requirements across four design artefacts required disciplined traceability. | Risk of missing requirements in design. Potential gaps in coverage. | Created requirement-to-interface and interface-to-ERD alignment tables. Verified each requirement appears in Use Case, Sequence, ERD and Interface designs. | Thabang Zitha | 2026-09-22 | Resolved
2026-09-20 | Unit 3 / Phase 2 | Stakeholder requested minor refinements to the working prototype during the presentation. | Required updates to prototype after demo. | Documented changes. | Thabang Zitha, Nyakallo Pali | 2026-09-22 | Resolved
2026-10-20 | Unit 4 / Phase 3 | Formal manual and regression testing of the complete prototype is not yet completed; SRS schedules it for Unit 5. | Could leave defects undiscovered if initial function checks are mistaken for formal test completion. | Run formal test cases for booking, conflict prevention, cancellation, payment preference, role access, CRUD and cross-application flows; record pass/fail evidence and retest fixes. | All members | Unit 5 testing period | Resolved
2026-10-20 | Unit 4 / Phase 3 | Automated appointment reminders were simplified to manual reminders via the manager dashboard. | Customers may not receive automatic 24-hour reminders, which may reduce the intended reduction in no-shows. | Clearly document the limitation and demonstrate the manual reminder process; only mark automated reminders complete if implemented and evidenced. | Nyakallo Pali, Thabang Zitha | Before final submission | Resolved
2026-10- | Unit 4 / Phase 3 | Connecting Flutter and ASP.NET Core to the same Supabase project while keeping database fields, booking statuses, dates and access permissions consistent. | Inconsistent fields, dates or status values could prevent bookings from displaying correctly in both applications. Incorrect queries or permissions could also delay integration. | Use the same Supabase project and database schema, standardise field names and booking statuses, verify access permissions, and test that records created in one application can be retrieved in the other. | Nyakallo Pali, Thabang Zitha | 2026-10-21 | Resolved
2026-10-24 | Unit 4 / Phase 3 | Some members required repeated reminders to complete assigned work. | Increased coordination work and risked delaying integration and documentation. | Held check-ins, reminded owners about tasks and used tracker entries to make work and pending deliverables visible. | All members; coordination by Goitseone Kgwele | Before final submission | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 4 / Phase 3 | Initial or updated SRS completed | Yes
Reporting period | 2026-10-01 to 2026-10-25 | Progress report updated | Yes
Overall phase status | Prototype implementation documented; final submission preparation ongoing | Individual contributions recorded | Yes
What was completed during this phase? | The Unit 4 SRS documents the shared Supabase backend (schema, relationships, authentication and RLS), Flutter Customer/Stylist screens and booking flows, and the ASP.NET Manager Portal. Initial function checks were recorded as Pass. The SRS illustrates shared booking submission/retrieval and booking status updates via Supabase, with screenshots. The team also recorded corrections for query filters, refresh behaviour, inconsistent status values and payment-method joins. | Stakeholder engagement recorded | Yes
What remains incomplete? | Final submission readiness remains open: confirm GitHub folder/version evidence, complete any outstanding regression and demonstration checks, rehearse the live presentation, and ensure project schedule/tracker screenshots are legible. Email reminders are manual; cross-app updates may require refresh; no online payment processing. | Challenges and actions updated | Yes
Why is it incomplete? | The SRS provides initial checks and screenshots, not an independently verified final test cycle. The GitHub and tracker screenshot placeholders are still present. Final live demonstration and any required submission steps have not yet occurred. | Group reflection completed | Yes
Which contributions were particularly important? | Flutter application: Bennet Linda and Nyakallo Pali. ASP.NET Manager Portal: Goitseone Kgwele, Thabang Zitha and Yamkela Mazamani. The shared Supabase backend and integration required cooperation across the team. Exact individual effort and commit attribution should be checked against evidence. | Microsoft Project updated | Yes
Were there participation concerns? | Yes, coordination challenges occurred: some members needed repeated reminders to complete assigned work. Regular check-ins and use of the tracker helped address delays and maintain accountability. | GitHub evidence available | Yes
What will the group improve in the next phase? | Verify the two shared processes, complete final checks, obtain missing screenshots, reconcile task completion against actual evidence, and rehearse the presentation. Address remaining limitations where feasible. | Confidential peer check completed | Yes
Main priority for the next phase | Finish final assessment readiness checks, prepare a live demonstration of Flutter, ASP.NET and shared Supabase records, and submit an accurate evidence-backed SRS and project records. |  | Yes

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 4 / Phase 3 | Length | Approximately 300–400 words in total.
Project title | Cutting Edge Salon Management & Booking System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | Our main learning was that a prototype is only useful when the mobile app, web portal and shared database work together. Implementing Flutter, ASP.NET Core and Supabase required the group to pay attention to matching field names, booking status values, date formats, record identifiers and user permissions. We also learned that initial function checks are not the same as formal manual and regression testing. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Our group configured the shared Supabase backend, developed the Flutter Customer/Stylist app and ASP.NET Manager Portal, and connected both applications to the same database. Our group checked important shared workflows, including booking request and manager approval, cancellation, stylist availability and service/price updates. Initial integration issues were recorded, corrected and checked again. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | The group faced two substantial challenges: maintaining consistent fields, dates, status names and permissions across Flutter, ASP.NET and Supabase; and ensuring assigned tasks were completed without repeated reminders. Cross-application records sometimes required query adjustments or manual refresh. The group also had to maintain traceability across the design artefacts. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Bennet Linda and Nyakallo Pali worked primarily on the Flutter Customer/Stylist application. Goitseone Kgwele, Thabang Zitha and Yamkela Mazamani worked on the ASP.NET Manager Portal. Integration with the shared Supabase database required cooperation between both groups; responsibilities were discussed at check-ins.
Did all members contribute fairly? Explain. | All five members had assigned responsibilities, but participation was not always equally prompt. Some members needed repeated reminders to complete their allocated work. The group addressed this through check-ins, clearer ownership, and the Project Progress Tracker. Precise individual contributions should be confirmed against submitted files and GitHub evidence.
How did the group handle disagreements or delays? | The group used discussions and regular reminders to resolve delays and encourage members to finish their responsibilities. Technical integration issues were handled by standardising booking status values, correcting query filters, and checking updated records again in the relevant application.
What did the group learn from the stakeholder? | We learned that the stakeholder values the "luxury" feel and wants it prominent in the mobile interface. The stakeholder confirmed that payment method selection is important for staff preparation. The stakeholder requested that the "Cut and Dye" service be prominently displayed on the Home screen. The stakeholder also asked that the cancellation flow be simple and clear for customers. During the prototype presentation on 20 September 2026, we learned that the stakeholder engages much more meaningfully when they can interact with a working system — they gave specific, actionable feedback on the prototype, including making "Cut and Dye" more prominent, improving the gallery update flow, and confirming the cancellation flow restores availability. We learned that the stakeholder appreciates being involved in design decisions and values tangible demonstrations.
Improvement action 1 for the next phase | Recheck booking, cancellation, one-active-booking protection, status approval, access controls and service updates with representative dummy data; identify outstanding issues clearly.
Improvement action 2 for the next phase | Review responsibilities and completion evidence at each group meeting, resolve unfinished work early, and verify the GitHub repository, tracker and demonstration materials before submission.
Priority for the next phase | Prepare a clear final demonstration showing at least two Flutter–Supabase–ASP.NET shared processes, honestly explain the manual reminder and refresh-based update limitations, and ensure every member can defend their contribution.